## Sheet1
Project Schedule Template
Task Name | Start Date | Due Date | Assigned Owner | Dependencies | Status
Finalize branding | 2001-08-01 | 2003-08-01 | Sarah | — | In Progress
Design homepage | 2004-08-01 | 2008-08-01 | David | Finalize branding | Not Started
Build homepage | 2009-08-01 | 2013-08-01 | Raj | Design homepage | Not Started
Write website content | 2005-08-01 | 2010-08-01 | Emma | Finalize branding | In Progress
SEO setup | 2011-08-01 | 2012-08-01 | Leo | Write website content | Not Started
Final testing | 2014-08-01 | 2015-08-01 | Team | Build homepage, SEO setup | Not Started
Go live | 2016-08-01 | 2016-08-01 | Sarah | Final testing | Not Started